## Sheet1
Epic | Feature | User Story | Priority | Sprint | Status | Estimate | Acceptence Criteria
User Authentication & Home | Homepage | As a user, I want to view the home page. | Must Have | Sprint 1 | Completed | 2 | Homepage should load with banner, featured items, and basic UI.
User Authentication & Home | Login | As a user, I want to securely log in to my account. | Must Have | Sprint 1 | Completed | 2 | User should be redirected to dashboard after successful login.
User Authentication & Home | Register | As a user, I want to register for a new account. | Must Have | Sprint 1 | Completed | 4 | User should get a confirmation after registration.
User Authentication & Home | Menu View | As a user, I want to view the restaurant’s menu. | Should Have | Sprint 1 | Completed | 2 | Menu should display categories and dishes.
User Authentication & Home | Logout | As a user, I want to log out of my account. | Must Have | Sprint 1 | Completed | 4 | User should be redirected to login page after logout.
Address Management | Dish Info | View detailed information about each dish | Should Have | Sprint 2 | Completed | 2 | Each dish should show description, price, and image.
Address Management | Add Address | Add a delivery address | Must Have | Sprint 2 | Completed | 2 | Address should be saved and shown in profile.
Address Management | Update Address | Update existing address | Should Have | Sprint 2 | Completed | 2 | Changes should reflect immediately on the profile.
Address Management | Add Multiple Addresses | Add multiple delivery addresses | Could Have | Sprint 2 | Completed | 3 | User can select from multiple addresses during checkout.
Address Management | Delete Address | Delete an address no longer used | Could Have | Sprint 2 | Completed | 2 | Address should be removed from profile.
Search & Cart | Search Food | Search for specific food items | Should Have | Sprint 2 | Completed | 3 | Results should display matching food items dynamically.
Search & Cart | Add to Cart | Add food items to cart | Must Have | Sprint 2 | Completed | 2 | Items should appear in cart with quantity adjustment.
Search & Cart | View Cart | View cart before checkout | Must Have | Sprint 2 | Completed | 1 | User should see itemized list with total.
Search & Cart | Remove from Cart | Remove food items from cart | Should Have | Sprint 2 | Completed | 2 | Removed items should no longer appear in cart.
Order & Checkout | Place Order | As a user, I want to place an order successfully. | Must Have | Sprint 3 | Completed | 8 | Order should be placed and confirmation shown.
Order & Checkout | Apply Coupon | As a user, I want to apply discount coupons. | Could Have | Sprint 3 | Completed | 3 | Discount should reflect in cart total.
Order & Checkout | Choose Payment Method | As a user, I want to choose payment method. | Must Have | Sprint 3 | Completed | 3 | User can choose UPI, card, or COD.
Order & Checkout | Make Payment | As a user, I want to complete online payment. | Must Have | Sprint 3 | Completed | 8 | Successful payment should redirect to success page.
Post-Order Features | Order Tracking | As a user, I want to track my order status. | Should Have | Sprint 4 | To Do | 3 | Live order status should be shown.
Post-Order Features | Order History | As a user, I want to view my order history. | Should Have | Sprint 4 | To Do | 2 | List of previous orders with details.
Post-Order Features | Rate Food | As a user, I want to rate the food I received. | Could Have | Sprint 4 | To Do | 2 | User can give stars and comments.
Post-Order Features | Customer Support | As a user, I want to contact support if there’s an issue. | Must Have | Sprint 4 | To Do | 3 | Chat or contact form should be available.
65
33

## Sheet2
Sprint 2 ¦ Project Status Report ¦ Sprint Start Date : 23/06/2025 and End date : 27/06/2025
Project Name : Food delivery website
Sprint Goal : Enhance the food ordering experience by enabling users to view detailed dish information, manage multiple delivery addresses,search for food items, and effectively use the shopping cart for order preparation
Sprint Summary
Planned Story Points: 33
Completed Story Points: 33
Carried Over Story Points: 0
Team total capacity: 144
Team actual capacity: 96
Velocity Achieved: 16.5
BAC = 2000 * 65 = 130000
Actual Cost = 75000
Earned value = 65000
Planned Value = 66000
SV = -1000
CV = -10000
EAC = 140000
VAC = -10000
TCPI = 1.181
ETC = 65000
CPI= 0.87
SPI=0.98