## sprint1
Sprint - Capacity Planning
1 week sprint
Team | Allocation | Standard hours | mon | tue | wed | thr | fri | sat | sun | Ideal total hours | Ceremonies | Net hours | velocity vs capcity |  |  | forecast velocity
Ankur | 100 | 4 | 2 | 2 | 2 | 2 | 0 |  |  | 8 | 3 | 5
Puneeth | 100 | 4 | 2 | 2 | 2 | 2 | 0 |  |  | 8 | 3 | 5 | Team full capacity |  | 56 | Team full capacity |  | 56
abhishek | 100 | 4 | 2 | 2 | 2 | 2 | 0 |  |  | 8 | 3 | 5
krishna | 100 | 4 | 2 | 2 | 2 | 2 | 0 |  |  | 8 | 3 | 5 | Sprint | velocity | available capacity | Sprint | velocity | available capacity
madhushree | 100 | 4 | 2 | 2 | 2 | 2 | 0 |  |  | 8 | 3 | 5 | 1 | 14 | 40 | 1 | 14 | 40
shalini | 100 | 4 | 2 | 2 | 2 | 2 | 0 |  |  | 8 | 3 | 5 | 2 | 19 | 56 | 2 | 19 | 56
darshan | 100 | 4 | 2 | 2 | 2 | 2 | 0 |  |  | 8 | 3 | 5 | 3 | ? | 56 | 3 | 16.5 | 56
brunda | 100 | 4 | 2 | 2 | 2 | 2 | 0 |  |  | 8 | 3 | 5 | 4 | ? | 56 | 4 | 16.5 | 56
[10 empty] | 64 |  | 40 | average velocity | 16.5
Ceremonies | mins | hours
Daily scrum meeting | 60 | 1
grooming | 0 | 0
sprint planning | 60 | 1
sprint review | 30 | 0.5
retrospect | 30 | 0.5
others | 0 | 0
| 180 | 3

## sprint2
Sprint - Capacity Planning
2 week sprint
Team | Allocation | Standard hours | mon | tue | wed | thr | fri | sat | sun | Ideal total hours | Ceremonies | Net hours | velocity vs capcity |  |  | forecast velocity
Ankur | 100 | 4 | 2 | 2 | 2 | 2 | 2 |  |  | 10 | 3 | 7
Puneeth | 100 | 4 | 2 | 2 | 2 | 2 | 2 |  |  | 10 | 3 | 7 | Team full capacity= |  | 56 | Team full capacity |  | 56
abhishek | 100 | 4 | 2 | 2 | 2 | 2 | 2 |  |  | 10 | 3 | 7
krishna | 100 | 4 | 2 | 2 | 2 | 2 | 2 |  |  | 10 | 3 | 7 | Sprint | velocity | available capacity | Sprint | velocity | available capacity
madhushree | 100 | 4 | 2 | 2 | 2 | 2 | 2 |  |  | 10 | 3 | 7 | 1 | 14 | 40 | 1 | 14 | 40
shalini | 100 | 4 | 2 | 2 | 2 | 2 | 2 |  |  | 10 | 3 | 7 | 2 | 19 | 56 | 2 | 19 | 56
darshan | 100 | 4 | 2 | 2 | 2 | 2 | 2 |  |  | 10 | 3 | 7 | 3 | ? | 56 | 3 | 16.5 | 56
brunda | 100 | 4 | 2 | 2 | 2 | 2 | 2 |  |  | 10 | 3 | 7 | 4 | ? | 56 | 4 | 16.5 | 56
[10 empty] | 80 |  | 56 | average velocity | 16.5
Ceremonies | mins | hours
Daily scrum meeting | 60 | 1 | [8 empty] | Fixed scope release
grooming | 0 | 0 | [7 empty] | Formula:PBI's (size)/velocity=number of sprints(needed for release) |  |  |  | 13.1515
sprint planning | 60 | 1
sprint review | 30 | 0.5
retrospect | 30 | 0.5 | [8 empty] | Fixed date release
others | 0 | 0 | [7 empty] | Fomula: number of sprints*velocity(lowest)=PBI's(needed for release) |  |  |  | 98 | 1-98 assured
| 180 | 3 | [7 empty] | Fomula: number of sprints*velocity(avg)=PBI's(needed for release) |  |  |  | 115.5 | 99-115.5 may be
[10 empty] | Fomula: number of sprints*velocity(best)=PBI's(needed for release) |  |  |  | 133 | 116-133 not possible